## Slide 1
[ FULL-BLEED FOTO WESTGATE I — Thomas R. Malthusstraat 5, Amsterdam ]
WESTGATE I — PARIS PROOF
Your single point of control — delivering Paris Proof with tenant PwC fully aware and aligned
Project Management Proposal · Prepared for Corum A.M. · July 2026
[C&W LOGO]

## Slide 2
EXECUTIVE SUMMARY — THE PROPOSAL ON ONE PAGE
Appoint C&W as your single point of control: we deliver Paris Proof
with PwC fully aware and aligned — you decide, we deliver
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
2
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
SITUATION
Corum owns Westgate I — a prime 27,000 m² Amsterdam office, fully let to PwC — and has committed to make the building Paris Proof. This is a binding contractual obligation, not an ambition.
COMPLICATION
The upgrade must happen inside a live, occupied building without losing PwC's confidence, within a fixed budget and against a hard sustainability deadline — while being steered from a distance by an owner whose core business is investment, not Dutch construction management.
QUESTION
How does Corum deliver Paris Proof and protect both the PwC tenancy and the asset's value, without being pulled into day-to-day tenant and project management in the Netherlands?
ANSWER
Appoint Cushman & Wakefield as your single point of control. We deliver the Paris Proof transformation end-to-end and keep PwC fully aware and aligned throughout — from a low-commitment preparatory phase to verified handover. One contact, one report, no surprises.

## Slide 3
CONTENTS
How this proposal is built
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
3
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
01
THE CASE FOR ACTION
Situation, complication
& our governing answer
02
WHAT WE TAKE
OFF YOUR PLATE
Managing PwC & organizing
the Paris Proof works
03
THE JOURNEY
Chronological roadmap,
phasing & planning
04
HOW WE STAY
IN CONTROL
Organisation, governance,
reporting & risk
05
WHY C&W, TEAM
& TRACK RECORD
Differentiation, team (t.b.d.)
& references
06
COMMERCIALS
& THE DECISION
Fee, the 2030 vision
& next steps

## Slide 4
01 — THE CASE FOR ACTION · SITUATION
You own a prime Amsterdam asset with a binding
Paris Proof commitment attached to it
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
4
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
THE ASSET
Westgate I — Thomas R. Malthusstraat 5, 1066 JR Amsterdam. A prime, single-tenant office building of ± 27,000 m² GFA.
THE TENANT
PwC occupies the building and is in full operation every working day. The tenant relationship is the value of the asset.
THE OWNER
Corum A.M. — an institutional investor steering the asset from a distance, focused on returns, not on day-to-day Dutch construction.
THE COMMITMENT
The building must be brought to Paris Proof. This is a hard contractual obligation with a fixed budget and a fixed horizon.
WHAT THIS MEANS FOR CORUM
Three assets are at stake in one building, at the same time:
• The physical asset and its value
• The PwC tenancy — and the lease that underpins your return
• Your reputation as a reliable, professional landlord
All three are exposed the moment work starts inside an occupied building.

## Slide 5
01 — THE CASE FOR ACTION · COMPLICATION
Three forces converge on one occupied building —
and all three touch your return
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
5
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
01
THE TENANT RISK
PwC keeps working while you rebuild
A previous Corum project (Rotterdam) showed how quickly insufficient communication erodes tenant trust. Disruption, noise and uncertainty can damage the relationship — and a damaged relationship puts lease renewal, and asset value, at risk.
02
THE DELIVERY RISK
Fixed budget, complex technique, live site
Paris Proof means a full climate-system transformation (see M3E's two scenarios). Executed floor-by-floor in an occupied building, on a fixed budget, this is unforgiving: every technical or sequencing mistake becomes visible to the tenant and expensive to the owner.
03
THE DEADLINE RISK
Paris Proof is contractual, not optional
The obligation is binding. Slippage is not a soft cost — it is a breach exposure. The programme must be driven to a hard finish line, with the critical path owned and defended from day one.
Left unmanaged, these three risks compound. Managed by one accountable party, they become a controlled programme.

## Slide 6
OUR GOVERNING ANSWER
Make Cushman & Wakefield your single
point of control in the Netherlands.
We deliver the entire Paris Proof transformation end-to-end and keep PwC fully aware and aligned at every step. You steer the asset; we run the works and the tenant relationship — and we bring you every decision, prepared, before it is needed.
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED

## Slide 7
01 — THE CASE FOR ACTION · OUR ANSWER
In practice, we take three things entirely off your plate
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
7
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
PwC FULLY AWARE
& ALIGNED
• One familiar point of contact for PwC
• PwC actively involved in decisions that affect them
• Continuous insight into progress & planning
• Timely notice of anything impacting operations
• PwC feels the project is fully under control
WE ORGANIZE THE
SUSTAINABILITY WORKS
• Translate M3E's design into deliverable scope
• Run the tender & select the contractor
• Direct and supervise the site
• Drive the programme to Paris Proof
• Own budget, quality, planning & risk
WE KEEP YOU IN
CONTROL FROM AFAR
• One contact, one monthly report
• Every key decision prepared in advance
• Full transparency on cost & progress
• Clear escalation lines to Corum
• No surprises — ever
Corum keeps the decisions that matter. We deliver the works and keep PwC fully aware and aligned — so nothing ever lands on Corum by surprise.

## Slide 8
01 — THE CASE FOR ACTION · THE PLAYING FIELD
Four parties, one hub: we connect Corum, PwC,
M3E and the contractor
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
8
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
THE PARTIES
CORUM A.M.
Owner / investor — sets objectives, holds the budget, makes the decisions.
PwC
Tenant — must keep operating; their experience defines success.
M3E
Technical advisor — develops the climate-system design (two scenarios).
CONTRACTOR
Executes the works — selected and managed through the tender.
C&W AS THE HUB
CORUM
PwC
M3E
CONTRACTOR
C&W
Single point
of control

## Slide 9
02 — WHAT WE TAKE OFF YOUR PLATE · THE TECHNIQUE
Two technical routes to Paris Proof — we make the choice
decision-ready for you
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
9
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
Based on M3E's scenario notes (9 Feb 2026). Our job is not to design — it is to turn this choice into a clear, costed, de-risked decision.
PREFERRED — LT-WKO + CLIMATE CEILINGS
• Full replacement of the gas installation
• Low-temperature thermal storage (WKO): warm & cold source
• Energy plant in the basement (heat pumps, buffers)
• Climate ceilings + new VAV (no induction) per floor
• New integral controls; energy metering per floor
• Phased floor-by-floor — building stays in use
• Future-proof: one intervention, done
ALTERNATIVE — AIR-WATER HP + VRF + RETAINED VAV
• Air-water heat pump for base heating (roof)
• Existing VAV induction units retained
• VRF system with convectors for zone control per floor
• New DX block replaces outdated cooling
• Fewer interventions on the office floors
• Hybrid system — careful controls integration needed
• Residual VAV life ± 6–9 yrs → a second intervention later
C&W's role: benchmark both routes on cost, disruption to PwC and long-term asset value — then bring Corum a single, recommended decision. Our management approach is robust for either scenario: phased, floor-by-floor, tenant-first.

## Slide 10
02 — WHAT WE TAKE OFF YOUR PLATE · DEEP DIVE 1 OF 2
We deliver the works with PwC fully aware and aligned —
so your tenant stays confident and your lease stays intact
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
10
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
From day one, PwC deals with one familiar C&W face. We keep the tenant actively involved in the decisions that affect them, with continuous insight into progress and planning and timely notice of anything that touches their operations. The outcome, in Corum's own words: PwC experiences full confidence that the project is under control.
ONE FAMILIAR INTERFACE
The Stakeholder Management PM owns the PwC relationship end-to-end — one consistent, familiar point of contact for everything that touches the tenant.
ACTIVELY INVOLVED IN DECISIONS
PwC is actively involved in the decision-making process on matters that affect them — briefed early, aligned before we act, never presented with a fait accompli.
CONTINUOUS INSIGHT & TIMELY NOTICE
Continuous insight into progress and planning, and timely communication of any change that impacts business operations — noise, access and disruption kept inside agreed windows.
FULL CONFIDENCE, PROTECTED VALUE
The outcome Corum asked for: PwC experiences full confidence that the project is under control. A confident tenant renews — protecting lease retention, income and exit value.

## Slide 11
02 — WHAT WE TAKE OFF YOUR PLATE · DEEP DIVE 2 OF 2
We organize the works — from M3E's design
to a building that is Paris Proof
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
11
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
C&W is the orchestrator of the transformation. We take M3E's technical concept and turn it into a scope that can be tendered, contracted, built and commissioned — floor-by-floor, on budget, to the Paris Proof standard. Corum gets a finished, verified building; not a construction site to supervise.
1 SCOPE
Translate M3E's chosen scenario into a clear, tenderable scope of work.
2 TENDER
Run a structured tender; select the contractor on price, quality and risk.
3 BUILD
Direct and supervise the site; phased, floor-by-floor, tenant-first.
4 COMMISSION
Test, commission and verify each floor before handing it back in use.
5 PARIS PROOF
Deliver the verified, Paris Proof building and a documented handover.
One accountable owner across all five steps. Corum never has to stitch together advisors, contractors and inspectors — that is our job.

## Slide 12
02 — WHAT WE TAKE OFF YOUR PLATE · WHAT MAKES IT WORK
Four principles turn a risky rebuild into a controlled programme
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
12
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
TENANT SATISFACTION FIRST
The tenant experience is the lead indicator of success. Everything — sequencing, timing, communication — is designed around keeping PwC operational and confident. The lesson from Rotterdam is built into how we work.
PHASED DELIVERY IN A LIVE BUILDING
Floor-by-floor execution: one zone temporarily out of use, tested and handed back before the next begins. The building keeps running; the programme keeps moving.
CLEAR GOVERNANCE & DECISION RIGHTS
Everyone knows who decides what, and when. PwC is involved where it matters, Corum decides the big calls, C&W runs the rest — with clean escalation lines.
NO SURPRISES
A live Risk Register from day one and decisions prepared in advance. Corum hears about issues as early intelligence, with an option to decide — never as a problem after the fact.

## Slide 13
03 — THE JOURNEY
From today to Paris Proof: the story of the next few years,
on one line
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
13
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
TODAY
Jul 2026
NDA signed, mandate confirmed. C&W becomes Corum's single point of control.
MOBILISE
Q3 2026
Preparatory phase: stakeholders mapped, PwC engaged, project organisation stood up.
DECIDE
Q4 2026
M3E scenario chosen with C&W's decision-ready recommendation; scope fixed.
TENDER
Q1–Q2 2027
Contractor selected on price, quality and risk. Works contracted.
BUILD
2027–2029
Floor-by-floor execution in the live building. PwC operational throughout.
PARIS PROOF
target
Verified handover. Asset compliant, tenant retained, value protected.
tijdlijn indicatief — jaartallen te valideren met M3E-ontwerpplanning, Paris Proof-deadline en Corum–PwC afspraken

## Slide 14
03 — THE JOURNEY · ENGAGEMENT MODEL
You commit in steps: start small, scale with confidence
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
14
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
PHASE 0
PREPARATORY ASSIGNMENT
A limited, low-commitment start: map all stakeholders, set up the project organisation, gather M3E's input, capture PwC's requirements. Deliverable: one integral project plan you can rely on.
PHASE 1
PM PREPARATION
Guide the technical design to a fixed scope, prepare the tender documents, run the tender and select the contractor.
PHASE 2
PM EXECUTION
Direct and supervise the works: floor-by-floor phasing, tenant communication, and control of budget, quality, planning and risk.
PHASE 3
BUILDING CONSULTANCY
Independent quality inspections during construction — an extra pair of expert eyes protecting Corum's interest on site.
Each phase is a separate assignment with its own scope, deliverables and fee. You are never asked to commit to the whole programme up front — you decide, phase by phase, on the strength of what we have delivered.

## Slide 15
03 — THE JOURNEY · PLANNING
The programme on a page — indicative, and ours to defend
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
15
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Q4 2027
2028
2029
NDA · mandate · award Phase 0
Phase 0 — preparatory → project plan
Scenario decision (M3E + C&W)
Technical design guided to fixed scope
Tender & contractor selection
Contracting
Execution — floor-by-floor (PM + inspections)
Commissioning & Paris Proof handover
Aftercare & fine-tuning
■ red = decision / milestone owned by C&W
indicatief — te valideren met M3E-ontwerpplanning, Paris Proof-deadline en Corum–PwC afspraken

## Slide 16
04 — HOW WE STAY IN CONTROL · ORGANISATION
Two project managers cover both sides of this project:
the diplomatic and the technical
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
16
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
CORUM A.M.
Client / Owner — decides
PwC
Tenant — kept operational & involved
STAKEHOLDER MANAGEMENT PM
Owns the PwC relationship:
communication · expectations · decisions
TECHNICAL PM
Owns the works:
technical coordination · site management ·
M3E alignment · tender & execution
M3E
Technical advisor / installation design
CONTRACTOR
Selected & managed via tender
One PM guards the relationship and the tenant experience; one guards the technique and the site. Together they are your single point of control — nothing falls between the diplomatic and the technical.

## Slide 17
04 — HOW WE STAY IN CONTROL · GOVERNANCE
Clear decision rights: you decide the big calls, we run
everything around them
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
17
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
DECISION AREA
CORUM
C&W
PwC / M3E
SITS WITH
Strategic & budget decisions
DECIDE
recommend
consult
CORUM
Scenario / design choice
DECIDE
recommend & prepare
input
CORUM
Tenant communication & impact
informed
MANAGE
involved
C&W
Contractor selection
approve
run & recommend
—
C&W→Corum
Day-to-day site & works
informed
DIRECT
execute
C&W
Risk & escalation
escalation point
OWN & flag early
—
C&W→Corum
The full project team is personally introduced to all parties at the outset — so every name has a face from day one.

## Slide 18
04 — HOW WE STAY IN CONTROL · REPORTING
You stay fully in control from Paris — on one page a month
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
18
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
Corum steers the asset from a distance. Our reporting is built for exactly that: one concise monthly report that tells you everything you need — and nothing you don't.
Every report answers four questions:
• Are we on schedule?
• Are we on budget?
• Is PwC satisfied?
• What decisions do you need to make next?
Detail sits in the appendix. Decisions come to you already prepared, with a recommendation.
MONTHLY ONE-PAGE REPORT [ dashboard mock-up ]
SCHEDULE
on track / at risk
[ ● ]
BUDGET
forecast vs. fixed
[ ● ]
TENANT (PwC)
satisfaction & issues
[ ● ]
RISK
top items · RAG
[ ● ]
DECISIONS DUE
prepared for Corum
[ ● ]
PROGRESS
floors complete
[ ● ]

## Slide 19
04 — HOW WE STAY IN CONTROL · RISK
We manage risk as asset-value protection — not as paperwork
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
19
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
A live Risk Register from day one: risks identified early, ownership assigned, mitigation agreed. Each risk is framed by what it threatens — the tenant, the budget or the deadline — the three things that drive Corum's return.
#
RISK
THREATENS
MITIGATION
OWNER
RAG
1
Tenant disturbance / PwC dissatisfaction
Tenancy
Floor-by-floor phasing, tenant comms plan, agreed working windows
SPM
●
2
Phasing conflicts between floors in a live building
Deadline
Integral phasing plan, buffer per floor, weekly look-ahead
TPM
●
3
WKO permits & source-drilling lead time (preferred)
Deadline
Early permit inventory & plan; applications started in Phase 1
TPM
●
4
Tender result exceeds fixed budget
Budget
Cost estimates at design milestones, VE options, market sounding
TPM
●
5
Controls / systems integration (esp. hybrid alt.)
Budget
Commissioning plan, integral controls party, test per floor
TPM
●
6
Slow owner/tenant decision-making
Deadline
Decision calendar; every decision prepared in advance by C&W
SPM
●

## Slide 20
05 — WHY C&W, TEAM & TRACK RECORD
Why Cushman & Wakefield — not a local project-management firm
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
20
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
WE SPEAK INVESTOR
As a global real estate adviser, we understand Corum's world: returns, lease value, exit. We manage the project in the language of asset value, not just square metres.
WE MANAGE CORPORATE OCCUPIERS
Managing demanding corporate tenants like PwC is core C&W business. We know how to keep a blue-chip occupier confident through disruptive works.
WE ARE ONE INTEGRATED PARTNER
Project & Development Services, cost management, building consultancy and market knowledge under one roof — one accountable partner, not a chain of sub-advisers.
WE ARE LOCAL, FOR A REMOTE OWNER
Feet on the ground in the Netherlands, reporting to an owner abroad. We are your eyes, ears and hands in Amsterdam — exactly the gap Corum needs filled.

## Slide 21
05 — TEAM
[ TEAMPAGINA — BEWUST LEEG GELATEN / IN TE VULLEN ]
21

## Slide 22
05 — WHY C&W, TEAM & TRACK RECORD
We have done exactly this: sustainability upgrades in
occupied, blue-chip buildings
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
22
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
[FOTO]
REFERENCE 1
Project name
Sustainability upgrade / renovation in an occupied office
Size · C&W role · outcome (tenant retained, on time, on budget)
[ in te vullen ]
[FOTO]
REFERENCE 2
Project name
Sustainability upgrade / renovation in an occupied office
Size · C&W role · outcome (tenant retained, on time, on budget)
[ in te vullen ]
[FOTO]
REFERENCE 3
Project name
Sustainability upgrade / renovation in an occupied office
Size · C&W role · outcome (tenant retained, on time, on budget)
[ in te vullen ]
[FOTO]
REFERENCE 4
Project name
Sustainability upgrade / renovation in an occupied office
Size · C&W role · outcome (tenant retained, on time, on budget)
[ in te vullen ]

## Slide 23
06 — COMMERCIALS & THE DECISION · FEE
A fee structured as a phased investment — low to start,
earned as we deliver
CUSHMAN & WAKEFIELD | CORUM A.M. · WESTGATE I
23
CORUM DECIDES · C&W DELIVERS · PwC ALIGNED
PHASE 0 — Preparatory assignment
Lump sum
€ [ • ]
PHASE 1 — PM Preparation
Fixed fee / monthly rate
€ [ • ]
PHASE 2 — PM Execution
Fixed fee / monthly rate
€ [ • ]
PHASE 3 — Building Consultancy (inspections)
Unit rate per inspection
€ [ • ]
RATE CARD — C&W PDS 2026
Project Manager € 145 / hr
Senior Project Manager € 155 / hr
Cost Manager € 145 / hr
Associate Director € 175 / hr
Partner € 250 / hr
[ tarieven excl. btw · inzet definitief met Frank ]
WHY THIS STRUCTURE WORKS FOR CORUM
• You commit phase by phase — the Phase 0 fee is small relative to the asset and the Paris Proof exposure it protects
• Design, calculations and specifications are by M3E (outside C&W scope) · DNR 2011 applicable
• [ verdere uitgangspunten & exclusies in te vullen met Frank ]

## Slide 24
06 — THE DECISION
Picture Westgate I in 2030
A Paris Proof building. PwC still in place, still confident, lease renewed. An asset whose value is protected and whose compliance is proven — delivered without Corum ever having to manage a Dutch building site or a tenant dispute. That is what a single point of control buys you.
THE DECISION WE ASK YOU TO MAKE NOW
1
Confirm the NDA (via Dentons)
in progress
2
Share the Corum–PwC agreement & Corum–M3E arrangement
upon NDA
3
Award Phase 0 — the preparatory assignment
July 2026
4
Kick-off & personal introduction of the full team
within 2 weeks
5
Integral project plan → decide on Phases 1–3
end of Phase 0
Sjoerd Bezemer · +31 (0)6 128 485 42 · sjoerd.bezemer@cushwake.com | Frank Okker — Head of PDS Netherlands