PROPOSAL.

TELEDYNE

Fit-out High Tech Campus 6, Eindhoven

Date:	8 July 2026

Contact:	Sjoerd Bezemer

Mobile:	+31 (0)6 128 485 42

Email:	sjoerd.bezemer@cushwake.com

Reykjavikstraat 1 | 3543 KH UTRECHT

SITUATION AND REQUEST.

Teledyne has recently leased approximately 1,200 m² at High Tech Campus 6 in Eindhoven. The programme comprises office space, a cleanroom and logistics space. The lease was arranged with the support of Cushman & Wakefield and delivery of the leased space to Teledyne has already taken place.

The current status of the project is as follows:

A test-fit has been developed based on a spatial Programme of Requirements (PoR); the spatial layout is well understood.

The technical Programme of Requirements is largely clear.

Several contractors and specialist lab-builders have been approached for pricing. Their feedback is that the available information is insufficient for a reliable quotation, or that quotations carry a significant risk premium due to the remaining uncertainties.

The target move-in date is April 2027.

You have asked us to submit a proposal for the first phase of our structured design-and-delivery process: the development of a project plan. This project plan will provide the structure, clarity and decision framework required to de-risk the next phases and to obtain reliable, comparable pricing from the market.

PROPOSAL.

Following our kick-off meeting at High Tech Campus Eindhoven, we propose to deploy a senior project manager, supported where required by our in-house MEP and cost specialists given the technical complexity of the cleanroom component. The senior project manager will act as your single point of contact and will report directly to Teledyne.

Phase 1 – Project Plan

The project plan will cover:

The full process from the current situation through to move-in in April 2027.

The project phasing: definition, concept design (SO), preliminary design (VO), final design (DO), tender and contracting, construction, and handover.

The key milestones and an overall project schedule aligned with the April 2027 move-in date.

An overview of outstanding information and decisions, with owners and deadlines.

The basis (scope, deliverables and organisation) for the design, engineering and tender phases.

To produce the project plan we will undertake the following activities:

Kick-off and site visit at High Tech Campus 6.

Review of the available documentation: test-fit, spatial and technical Programme of Requirements, and the delivery documentation of the leased space.

Working sessions with the Teledyne stakeholders to validate ambitions, budget framework and schedule constraints.

Assessment of the open technical questions (with emphasis on the cleanroom and MEP scope) that currently prevent reliable contractor pricing.

Drafting of the project plan, a joint review session, and issue of the final project plan.

NEXT STEPS AFTER THE PROJECT PLAN.

The project plan forms the basis for the subsequent phases of our structured design-and-delivery process. Upon completion of the project plan, we can support Teledyne with the following steps:

Validate and complete the spatial and technical Programme of Requirements.

Develop a concept design (SO) with sufficient detail to lock down the key design decisions.

Advance to a preliminary design (VO), including technical engineering.

Develop a final design (DO) with all information ready for tender.

Organise and manage the tender and advise on the right parties to contract.

Advise on contracting the selected contractor(s).

Manage the construction phase as Project Manager and Site Manager, including chairing construction meetings, planning and quality control, progress reporting and periodic photo reporting.

Organise the handover, manage the completion of any remaining points and collect all as-built documentation, guarantees and maintenance instructions.

Cushman & Wakefield can support this full trajectory with its multidisciplinary in-house team: Design, Architecture, Engineering, Project Management, Cost Management and Site Management. Each subsequent phase will be quoted separately; the project plan provides the scope definition on which those fee proposals will be based, so that Teledyne maintains full control over commitments per phase.

FEE.

For the development of the project plan (Phase 1) we estimate the following effort:

| Role | Hours | Rate (EUR/h) | Amount (EUR) |
| --- | --- | --- | --- |
| Project manager sr. | 40 | 155,- | 6.200,- |
| MEP consultant | 8 | 175,- | 1.400,- |
| Cost consultant | 8 | 175,- | 1.400,- |
| Total (fixed fee, excl. VAT) | 56 |  | 9.000,- |

We offer Phase 1 for a fixed fee of EUR 9.000,- excluding VAT, including travel and accommodation expenses within the Netherlands.

SCHEDULE.

Once the signed proposal has been returned to us, we can start the work within two weeks. The project plan will be delivered within four weeks of the start.

Based on our knowledge and experience, and working back from the target move-in date of April 2027, we currently anticipate the following indicative durations per project phase. The definitive schedule will be developed as part of the project plan.

| Phase | Indicative duration |
| --- | --- |
| Project plan (this proposal) | 4 weeks |
| Validation and completion of the PoR | 2 weeks |
| Concept design (SO) | 6 weeks |
| Preliminary design (VO), incl. technical engineering | 8 weeks |
| Final design (DO), ready for tender | 8 weeks |
| Tender and contracting | 8 weeks |
| Work preparation / engineering by contractor(s) | 6 weeks |
| Construction, incl. cleanroom fit-out | 20 weeks |
| Handover and move-in | April 2027 |

RATES.

We apply the following hourly rates (PDS 2026) in EUR, which will also form the basis for the fee proposals of the subsequent phases:

| Role | Rate (EUR/h) |
| --- | --- |
| Project manager jr. | 125,- |
| Project manager | 140,- |
| Project manager sr. | 155,- |
| Site manager | 140,- |
| Site manager sr. | 155,- |
| Building surveyor jr. | 125,- |
| Building surveyor | 140,- |
| Building surveyor sr. | 155,- |
| Cost consultant | 175,- |
| MEP consultant | 175,- |
| Technical designer sr. | 135,- |
| Architect jr. | 110,- |
| Architect | 125,- |
| Architect sr. | 135,- |
| Associate Architect | 150,- |
| Interior Architect | 120,- |
| Interior Architect sr. | 135,- |
| Consultant sustainability | 135,- |
| Consultant sustainability sr. | 145,- |
| Associate Director | 175,- |
| Partner | 225,- |

INVOICING.

We will invoice the fixed fee for Phase 1 upon delivery of the project plan. We expect full payment of our invoice within 30 days of the invoice date. If you require a PO number on our invoice, or if the invoicing details need to be adjusted, please let us know.

CLIENT.

Teledyne

Attn. Mr. P. Kilkens, Vice President Global Operations

High Tech Campus 6, Eindhoven

[invoicing entity and address to be confirmed]

TERMS AND CONDITIONS.

De Nieuwe Regeling 2011 (DNR 2011) applies to our proposal. A copy of the DNR 2011 is enclosed with this proposal.

All amounts stated are exclusive of VAT and inclusive of travel and accommodation expenses within the Netherlands.

For our privacy policy, please refer to our website: https://www.cushmanwakefield.com/en/emea-and-california-privacy-notice

Thank you for your interest in our services. We hope that our proposal meets your expectations. Please do not hesitate to contact us if you have any questions or require additional information.

If you agree with the content of this proposal and wish to commission these services, we kindly request that you return the signed proposal to us. Once approved and signed, we can start the work within two weeks.

| Kind regards, | For approval: |
| --- | --- |
| Cushman & Wakefield Netherlands B.V. | Teledyne |
| Project & Development Services |  |
| i/o | Date: ……… - ……… - ……… |
| Annelou de Groot |  |
| Head of The Netherlands | (Name + signature of authorised signatory) |

Appendices:

DNR 2011

C&W Capability Statement Consultancy & Design