## Slide 1
[ FULL-BLEED FOTO WESTGATE I — Thomas R. Malthusstraat 5, Amsterdam ]
WESTGATE I — PARIS PROOF
Project Management Proposal
Prepared for Corum A.M. · July 2026
[C&W LOGO]

## Slide 2
CONTENTS
CONTENTS
2
CUSHMAN & WAKEFIELD | CORUM A.M.
01
INTRODUCTION &
UNDERSTANDING
Cover letter, the project,
two Paris Proof scenarios
02
OUR APPROACH
Role, success factors,
phased plan & planning
03
ORGANISATION &
GOVERNANCE
Two-PM model, governance,
risk management
04
TEAM &
TRACK RECORD
Team (t.b.d.),
references
05
FEE &
NEXT STEPS
Fee structure per phase,
next steps

## Slide 3
01 — INTRODUCTION
COVER LETTER & EXECUTIVE SUMMARY
3
CUSHMAN & WAKEFIELD | CORUM A.M.
Dear Dirk, dear Marcus,
Thank you for the open discussion on 2 July. Cushman & Wakefield is pleased to present our proposal to act as project manager on behalf of Corum for the Paris Proof upgrade of Westgate I — a technically complex programme in a fully occupied building, where tenant satisfaction is as important as technical delivery.
[ korte alinea's — definitieve brieftekst volgt ]
placeholder: brieftekst ± 120 woorden
UNDERSTANDING
Paris Proof is a hard contractual agreement. Works in a live building with PwC as tenant. M3E develops the technical design; contractor via tender.
APPROACH
Start small with a preparatory assignment; then three assignments: PM Preparation, PM Execution and Building Consultancy. Two complementary project managers.
COMMITMENT
Proactive communication, transparent decision-making, no surprises. We prepare every key decision so Corum decides well-informed and PwC keeps full confidence.
SJOERD BEZEMER
Associate — Business Development / Senior Project Manager
M +31 (0)6 128 485 42 · sjoerd.bezemer@cushwake.com
FRANK OKKER
Head of Project & Development Services Netherlands
[ handtekening / foto placeholder ]

## Slide 4
01 — INTRODUCTION
UNDERSTANDING THE PROJECT
4
CUSHMAN & WAKEFIELD | CORUM A.M.
BUILDING
Westgate I, Thomas R. Malthusstraat 5, 1066 JR Amsterdam
SIZE
± 27,000 m² GFA — office
OWNER
Corum A.M.
TENANT
PwC — building in full operation
OBJECTIVE
Technically upgrade to Paris Proof — hard contractual agreement
DESIGN
M3E develops technical design; scope fixed, contractor via tender
STAKEHOLDER MAP
CORUM
(owner / client)
PWC
(tenant)
C&W
(project manager)
M3E
(technical advisor)
CONTRACTOR
(via tender)
wireframe: verbindingslijnen + rollen in design uitwerken
KEY MESSAGE — Sustainability upgrade of a fully occupied building:
floor-by-floor delivery, tenant experience is the measure of success.

## Slide 5
01 — INTRODUCTION
TWO ROUTES TO PARIS PROOF
5
CUSHMAN & WAKEFIELD | CORUM A.M.
Based on the M3E scenario notes (9 Feb 2026) shared by Corum — summary of both options
PREFERRED — LT-WKO + CLIMATE CEILINGS
• Full replacement of gas-fired installation
• Low-temperature thermal storage (WKO): warm & cold source
• Energy plant in basement (heat pumps, buffers)
• Climate ceilings + new VAV (no induction) per floor
• New integral building controls, energy metering per floor
• Phased floor-by-floor — building stays operational
• Future-proof: one intervention, done
ALTERNATIVE — AIR-WATER HP + RETAIN VAV + VRF
• Air-water heat pump for base heating (roof)
• Existing VAV induction units retained
• VRF system with convectors as zone control per floor
• New DX block replaces outdated cooling
• Limited interventions on office floors
• Hybrid system — careful controls integration required
• Residual life VAV ± 6–9 yrs → second intervention later
Our project management approach is robust for either scenario — phased, floor-by-floor, tenant-first.

## Slide 6
02 — OUR APPROACH
THE ASSIGNMENT & OUR ROLE
6
CUSHMAN & WAKEFIELD | CORUM A.M.
PROJECT MANAGER ON BEHALF OF THE OWNER
C&W acts as project manager on behalf of Corum during preparation and execution: representing Corum's interests and ensuring effective collaboration between tenant, technical advisor and contractor.
We proactively anticipate key decisions by preparing them thoroughly in advance — Corum is well-advised at every stage, and PwC experiences full confidence that the project is under control.
1
Represent Corum's interests towards all parties
2
Coordinate communication between tenant, advisor & contractor
3
Monitor planning, budget, quality and risks
4
Manage the tender and contractor selection
5
Manage the execution phase, floor-by-floor
6
Ensure transparent decision-making throughout

## Slide 7
02 — OUR APPROACH
KEY SUCCESS FACTORS
7
CUSHMAN & WAKEFIELD | CORUM A.M.
TENANT SATISFACTION FIRST
Tenant satisfaction is central to Corum's objectives. A previous project (Rotterdam) showed how insufficient communication erodes trust — we put the tenant experience at the heart of planning and communication.
PHASED DELIVERY IN A LIVE BUILDING
Floor-by-floor execution: one zone temporarily out of use, handed back before the next starts. The building remains operational throughout.
CLEAR GOVERNANCE
PwC actively involved in decision-making, continuous insight into progress and planning, timely communication of impact on business operations, clear escalation lines, team personally introduced at the outset.
NO SURPRISES
Risk Register from day one: risks identified early, ownership assigned, mitigation agreed. Transparent reporting on budget and planning.

## Slide 8
02 — OUR APPROACH
A PHASED APPROACH — START SMALL, SCALE WITH CONFIDENCE
8
CUSHMAN & WAKEFIELD | CORUM A.M.
PHASE 0
PREPARATORY ASSIGNMENT
Limited assignment: map all stakeholders, set up project organisation, gather input from M3E, identify tenant requirements → integral project plan.
PHASE 1
PM PREPARATION
Guide technical design, fix scope, prepare tender documents, run tender and contractor selection.
PHASE 2
PM EXECUTION
Site & execution management, floor-by-floor phasing, progress/budget/risk control, tenant communication.
PHASE 3
BUILDING CONSULTANCY
Independent quality inspections during construction.
Following the preparatory assignment, we propose three separate assignments — PM Preparation, PM Execution and Building Consultancy — each with its own scope, deliverables and fee. Corum decides per phase.

## Slide 9
02 — OUR APPROACH
PROCESS PLANNING (INDICATIVE)
9
CUSHMAN & WAKEFIELD | CORUM A.M.
Q3 2026
Q4 2026
Q1 2027
Q2 2027
Q3 2027
Q4 2027
2028
NDA · proposal · award Phase 0
Phase 0 — preparatory → project plan
Technical design (M3E) — guided by C&W
Tender & contractor selection
Contracting
Execution — floor-by-floor (PM + inspections)
Handover · aftercare · fine-tuning
wireframe: balkenplanning indicatief — te valideren met M3E-ontwerpplanning en Corum–PwC afspraken
◆ = decision milestone Corum

## Slide 10
03 — ORGANISATION
PROJECT ORGANISATION — THE TWO-PM MODEL
10
CUSHMAN & WAKEFIELD | CORUM A.M.
CORUM A.M.
Client / Owner
PWC
Tenant — involved in governance
STAKEHOLDER MANAGEMENT PM
Tenant relations · communication ·
decision-making
TECHNICAL PM
Technical coordination · site mgmt ·
M3E alignment · tender & execution
M3E
Technical advisor / installation consultant
CONTRACTOR
Selected via tender
wireframe: verbindingslijnen + eventueel cost management / inspecties toevoegen in design
Two complementary project managers: one guards the relationship and the tenant experience, one guards the technique and the site — the technical and diplomatic sides of this project are equally covered.

## Slide 11
03 — ORGANISATION
GOVERNANCE & COMMUNICATION
11
CUSHMAN & WAKEFIELD | CORUM A.M.
STEERING MEETING
Corum · C&W (· PwC where relevant)
Monthly — direction, decisions, escalation
PROJECT TEAM MEETING
C&W · M3E (· contractor from execution)
Bi-weekly — progress, planning, actions
TENANT ALIGNMENT
Stakeholder PM · PwC facility/leadership
Structured cadence + ad-hoc at impact
SITE MEETING
Technical PM · contractor
Weekly during execution
GOVERNANCE PRINCIPLES
• PwC actively involved in the decision-making process
• Continuous insight into progress and planning
• Timely communication of changes impacting business operations
• Clear escalation lines
• Full project team personally introduced to all parties at the outset
REPORTING
Monthly progress report: planning · budget · quality · risks · tenant impact — one page for Corum management, detail in appendix. [ dashboard mock-up placeholder ]

## Slide 12
03 — ORGANISATION
RISK MANAGEMENT — NO SURPRISES
12
CUSHMAN & WAKEFIELD | CORUM A.M.
We work with a Risk Register from the very start: risks identified early, ownership assigned, mitigation agreed — surprises during execution avoided as much as possible.
#
RISK (EXAMPLES)
IMPACT
MITIGATION
OWNER
RAG
1
Tenant disturbance / complaints during works
High
Floor-by-floor phasing, tenant comms plan, agreed working windows
SPM
●
2
Phasing conflicts between floors in a live building
High
Integral phasing plan, buffer per floor, weekly look-ahead
TPM
●
3
WKO permits & source drilling lead time (preferred scenario)
Med
Early permit inventory & planning, start applications in Phase 1
TPM
●
4
Tender result exceeds budget
Med
Cost estimate at design milestones, VE-options, market sounding
TPM
●
5
Controls/systems integration (esp. hybrid alternative)
Med
Commissioning plan, integral controls party, test per floor
TPM
●
6
Decision-making lead time owner/tenant
Med
Decision calendar, decisions prepared in advance by C&W
SPM
●
wireframe: voorbeeldrisico's — definitieve register in fase 0 opstellen; RAG-bolletjes in design

## Slide 13
04 — TEAM
[ TEAMPAGINA — BEWUST LEEG GELATEN / IN TE VULLEN ]
13

## Slide 14
04 — TEAM & TRACK RECORD
TRACK RECORD — COMPARABLE PROJECTS
14
CUSHMAN & WAKEFIELD | CORUM A.M.
[FOTO]
REFERENCE 1
Project name
Sustainability upgrade / renovation in occupied office
Size · role C&W · result
[ in te vullen ]
[FOTO]
REFERENCE 2
Project name
Sustainability upgrade / renovation in occupied office
Size · role C&W · result
[ in te vullen ]
[FOTO]
REFERENCE 3
Project name
Sustainability upgrade / renovation in occupied office
Size · role C&W · result
[ in te vullen ]
[FOTO]
REFERENCE 4
Project name
Sustainability upgrade / renovation in occupied office
Size · role C&W · result
[ in te vullen ]
selectiecriteria: verduurzaming/renovatie in gebruik zijnd kantoor · institutionele eigenaar · huurdercommunicatie

## Slide 15
05 — FEE & NEXT STEPS
FEE PROPOSAL
15
CUSHMAN & WAKEFIELD | CORUM A.M.
PHASE 0 — Preparatory assignment
Lump sum
€ [ • ]
PHASE 1 — PM Preparation
Fixed fee / monthly rate
€ [ • ]
PHASE 2 — PM Execution
Fixed fee / monthly rate
€ [ • ]
PHASE 3 — Building Consultancy (quality inspections)
Unit rate per inspection
€ [ • ]
RATE CARD (REFERENCE)
Senior Project Manager € 145 / hr
Project Manager € 135 / hr
Technical PM € 135 / hr
Cost Manager € 125 / hr
Site Manager € 120 / hr
[ tarieven & inzet definitief met Frank ]
ASSUMPTIONS & EXCLUSIONS
• Each phase is a separate assignment — Corum decides per phase
• Technical design, calculations and specifications by M3E (outside C&W scope)
• DNR 2011 applicable · [ verdere uitgangspunten in te vullen ]

## Slide 16
05 — FEE & NEXT STEPS
NEXT STEPS
16
CUSHMAN & WAKEFIELD | CORUM A.M.
1
NDA via Dentons — signed
in progress
2
Insight into Corum–PwC agreement & Corum–M3E arrangement
upon NDA
3
Confirmation of Phase 0 — preparatory assignment
July 2026
4
Kick-off & personal introduction of the full project team
within 2 weeks of award
5
Integral project plan → decision on Phase 1–3 assignments
end of Phase 0
Sjoerd Bezemer · +31 (0)6 128 485 42 · sjoerd.bezemer@cushwake.com | Frank Okker — Head of PDS Netherlands